## Projects
ID | Type | Description
P1 | Active Project | 8x25 QPR w/C+G
P2 | Active Project | 8x30 Tablet with IDH
P3 | Active Project | 8130 TD-SCDMA with IDH
P4 | Active Project | 8230 W+G with IDH
P5 | Active Project | 8x26 SKU1/2 w/C+G DSDA
P6 | Active Project | 8930 TDD LTE w/IDH
P7 | Active Project | 8x10 SKU1/2 w/C+G DSDA
P8 | Active Project | 8926 TDD LTE CMCC
P9 | Projects in Maintainence | 8x25 ICS and 7x27A
P10 | None-project | Test Dry run
P11 | None-project | FUT issue support
P12 | None-project | CE RV issue support
P13 | None-project | Tool Development

## Tasks
Task Type | Sub-type | Description | Base Task | Task ID | Task Description
Target/Release | T1 | Integration Test Support | Test Case Execution | T1a | Manual Test Execution/Verification
|  |  |  | T1b | Auto Test Execution/Verification
|  |  |  | T1c | Test Dry run
| T2 | Product Test Support (Focus on Test development and Execution) | Test Case Review | T2a | Test Case Execution
|  |  |  | T2b | Issues Reproduction/Verification
|  |  |  | T2c | Test Case/Issue Review
|  |  |  | T2d | Test Script Development
| T3 | Product Test Support (Focus on Test Managenent and Execution) | Test Case Review | T3a | Test Cases Review
|  |  |  | T3b | Test Cases Execution
|  |  |  | T3c | Alpha/IDH Issue Reproduction and Verification
|  |  |  | T3d | FUT Issue Reproduction and Verification
|  |  |  | T3e | RV CR Reproduction
|  |  |  | T3f | Alpha Issue Tracking and Synchronization
Software development and test | T4 | R&D Test Support (Focus on Feature Test) | Test Case Review | T4a | Test Case Execution
|  |  |  | T4b | Issue or CR Reproduction
|  |  |  | T4c | Test Case Review
|  |  |  | T4d | Test Script Development
| T5 | Application Development Support (including APP/MM) | Bug fix | T5a | UI Specification and Related Documents for New Features
|  |  |  | T5b | Feature Development/Integration
|  |  |  | T5c | Bug Fix
|  |  |  | T5d | Unit Test Case Development
|  |  |  | T5e | QSST Tool Development (New Feature)
| T6 | Platform Development Support (Including BSP/Modem) | Power Test Development and Power Sanity Test Execution (Automation) | T6a | Modem Auto Test Execution and/or Test Report Review
|  |  |  | T6b | Sanity Test Execution
|  |  |  | T6c | Monkey Test Execution (Automation)
|  |  |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation)
|  |  |  | T6e | Bug Fix
Hardware Development and test | T7 | Hardware Validation Test Support | Test Case Execution | T7a | Test Case Development
|  |  |  | T7b | Test Case Execution
|  |  |  | T7c | Issue or CR Reproduction
|  |  |  | T7d | Test Case Review
| T8 | Component Verification Test Support | Test Case Execution | T8a | Test Case Development
|  |  |  | T8b | Test Case Execution
|  |  |  | T8c | Test Report Review
| T9 | Build Support (Factory Tool Development, Factory Onsite Support and Hardware Documentation) | Test Case Execution | T9a | BRF Package (including QRD-QDART installer) Test Case Execution
|  |  |  | T9b | Build BRFs Packages for Release
|  |  |  | T9c | Prepare BRFs Documents for Release
|  |  |  | T9d | BRF Package Validation
|  |  |  | T9e | QRD and IDH Project Build Production Support
|  |  |  | T9f | QRD Hardware Lab board Validation Support
|  |  |  | T9g | QRD Hardware Document Support
|  |  |  | T9h | IDH Hardware Document Support
|  |  |  | T9i | QRD Hardware Document Release Process Support
|  |  |  | T9j | QRD Hardware Qwiki Maintenance

## Deliverables
Deliverable ID | Milestone Deliverable Points (MDP) |  |  | Deliverable description
| 2013 April | 2013 May | 2013 June
| M1 | M2 | M3
D1 | 52400 | 74800 | 74800 | Integration test related reports
D2 | 41850 | 53300 | 42250 | Product test related reports (focus on test development and execution)
D3 | 56325 | 100680 | 82000 | Product test related reports (focus on test management and execution)
D4 | 51000 | 76500 | 93800 | R&D test support (focus on feature test)
D5 | 340 | 390 | 390 | Application Processor (AP) development related reports and documents
D6 | 266 | 474 | 659 | Platform (Modem and BSP) development related reports
D7 | 9745 | 9480 | 9648 | Hardware validation test related reports
D8 | 32874 | 30080 | 29960 | Components verification test related reports
D9 | 12018 | 11611 | 7648 | Build support (document and tool) related reports, document and services

## Summary
Deliverable ID | Milestone Deliverable Points (MDP) |  |  | Executed Tasks |  |  | Complete Rate
| 2013 April | 2013 May | 2013 June | 2013 April | 2013 May | 2013 June
| M1 | M2 | M3 | M1 | M2 | M3
D1
D2
D3
D4
D5 | 340 | 390 | 390 | 373 | 1268.5 | 816.5 | 219.5%
D6 | 266 | 474 | 659 | 284.5 | 276 | 227 | 56.29%
D7
D8
D9

## weekly_report
No. | Week | Project ID | Deliverable ID | Work description | Task ID | Manager | Status | MDP | Risk | Mitigation plan | Comment
Yu Chuanchun | 0712 | P13 | D5 | Fix Bug:After ME reboot unnormal, Qsst will restart, but it stop quickly. | T5e | Mao,Xiaodong | Done | 1 | No | No | No
Yu Chuanchun | 0712 | P13 | D5 | Fix bug:Can't stop qsst from notificationbar after ME reboot and qsst restart. | T5e | Mao,Xiaodong | Done | 1 | No | No | No
Yu Chuanchun | 0712 | P13 | D5 | Fix bug:If repeat case that include reboot case or case crash when running, the repeat cann't continue. | T5e | Mao,Xiaodong | Done | 1 | No | No | No
Yu Chuanchun | 0712 | P13 | D5 | Fix bug :In the report, the crashed case will show as SUCCESS when QSST continue to run the next case after crash reset. | T5e | Mao,Xiaodong | Done | 1 | No | No | No
Yu Chuanchun | 0712 | P13 | D5 | Fix bug: case.call() method need return whether case running success. | T5e | Mao,Xiaodong | Done | 1 | No | No | No
Yu Chuanchun | 0712 | P13 | D5 | Add call case doc. | T5e | Mao,Xiaodong | Done | 1 | No | No | No
Yu Chuanchun | 0712 | P13 | D5 | Write CMCC MTBF case. | T5e | Mao,Xiaodong | Ongoing | 1 | No | No | No
Note on I1: MDP = Weight * Workload
Note on J1: Please identify any potential risks in terms of meeting project schedule

## D5
Acceptance Criteria for Project Deliverable D5 (M1, M2 and M3) | [7 empty] | 2013-04-30 | 2013-05-31 | 2013-06-30 | 4/1/2013 - 6/30/2013 | April |  |  |  |  | May |  |  |  | June |  |  |  | Wk 22
Scope: Application Development Support (including APP/MM) | [11 empty] | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | 5/27/2013~5/31/2013
Base Task: Bug Fix | [11 empty] | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06 | 2013-05-13 | 2013-05-20 | 2013-05-27 | 2013-06-03 | 2013-06-10 | 2013-06-17 | 2013-06-24
ID | Project (PL/CPL) | Task ID | Task Description | Weight | M1 Workload | M2 Workload | M3 Workload | M1 MDP | M2 MDP | M3 MDP | Project MDP | 2013-04-01: M1 work assgined; 2013-05-06: M2 work assgined; 2013-06-03: M3 work assgined | Assigned Tasks | Executed Tasks
P1 | 8x25 QPR w/C+G | T5c | Bug Fix | 1 | 40 | 20 | 20 | 40 | 20 | 20 | 80 | 2013-04-01: 16; 2013-04-08: 16; 2013-04-15: 16; 2013-04-22: 16; 2013-04-29: 16 |  | 0
P1 | [25 empty] | 0
P2 | 8x30 Tablet with IDH | T5a | UI Specification and Related Documents for New Features | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P2 |  | T5b | Feature Development/Integration | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P2 |  | T5c | Bug Fix | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P2 |  | T5d | Unit Test Case Development | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P3 | 8130 TD-SCDMA with IDH | T5a | UI Specification and Related Documents for New Features | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P3 |  | T5b | Feature Development/Integration | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P3 |  | T5c | Bug Fix | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P3 |  | T5d | Unit Test Case Development | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P4 | 8230 W+G with IDH | T5a | UI Specification and Related Documents for New Features | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P4 |  | T5b | Feature Development/Integration | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P4 |  | T5c | Bug Fix | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P4 |  | T5d | Unit Test Case Development | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P5 | 8x26 SKU1/2 w/C+G DSDA | T5a | UI Specification and Related Documents for New Features | 2 | 30 | 0 | 0 | 60 | 0 | 0 | 390 | 2013-04-01: 17; 2013-04-08: 12 |  | 0
P5 |  | T5b | Feature Development/Integration | 4 | 0 | 30 | 0 | 0 | 120 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P5 |  | T5c | Bug Fix | 1 | 10 | 40 | 100 | 10 | 40 | 100 |  | 2013-04-01: 2; 2013-04-08: 2 |  | 0
P5 |  | T5d | Unit Test Case Development | 2 | 0 | 20 | 10 | 0 | 40 | 20 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P5 | [25 empty] | 0
P6 | 8930 TDD LTE w/IDH | T5a | UI Specification and Related Documents for New Features | 2 | 30 | 0 | 0 | 60 | 0 | 0 | 440 | 2013-04-01: 12; 2013-04-08: 12 |  | 0
P6 |  | T5b | Feature Development/Integration | 4 | 30 | 0 | 0 | 120 | 0 | 0 |  | 2013-04-01: 24; 2013-04-08: 24 |  | 0
P6 |  | T5c | Bug Fix | 1 | 20 | 80 | 100 | 20 | 80 | 100 |  | 2013-04-01: 4; 2013-04-08: 4; 2013-05-06: 3; 2013-05-13: 3 | 3 | 0
P6 |  | T5d | Unit Test Case Development | 2 | 0 | 30 | 0 | 0 | 60 | 0 |  | 0 | 0 |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
0
P7 | 8x10 SKU1/2 w/C+G DSDA | T5a | UI Specification and Related Documents for New Features | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P7 |  | T5b | Feature Development/Integration | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P7 |  | T5c | Bug Fix | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P7 |  | T5d | Unit Test Case Development | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
0
P8 | 8926 TDD LTE CMCC | T5a | UI Specification and Related Documents for New Features | 2 | 0 | 0 | 30 | 0 | 0 | 60 | 120 | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P8 |  | T5b | Feature Development/Integration | 4 | 0 | 0 | 10 | 0 | 0 | 40 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P8 |  | T5c | Bug Fix | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P8 |  | T5d | Unit Test Case Development | 2 | 0 | 0 | 10 | 0 | 0 | 20 |  | 2013-04-01: 0; 2013-04-08: 0 |  | 0
P13 | Tool Development | T5e | QSST Tool Development (New Feature) | 2 | 15 | 15 | 15 | 30 | 30 | 30 | 90 | 10 | 10 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 7
Milestone Deliverable Points (MDPs) | [7 empty] | 340 | 390 | 390 | 1120 | 85 | 80 | 20 | 20 | 20 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 12 | 7

## D6
Acceptance Criteria for Project Deliverable D6 (M1, M2 and M3) | [7 empty] | 2013-04-30 | 2013-05-31 | 2013-06-30 | 4/1/2013 - 6/30/2013 | April |  |  |  |  | May |  |  |  | June |  |  |  | Wk 22
Scope: Platform Development Support (Including BSP/Modem) | [11 empty] | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | 5/27/2013~5/31/2013
Base Task: Power Test Case Development and Power Sanity Test Execution (Automation) | [11 empty] | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06 | 2013-05-13 | 2013-05-20 | 2013-05-27 | 2013-06-03 | 2013-06-10 | 2013-06-17 | 2013-06-24
ID | Project (PL/CPL) | Task ID | Task Description | Weight | M1 Workload | M2 Workload | M3 Workload | M1 MDP | M2 MDP | M3 MDP | Project MDP | 2013-04-01: M1 work assgined; 2013-05-06: M2 work assgined; 2013-06-03: M3 work assgined | Assigned Tasks | Executed Tasks
P1 | 8x25 QPR w/C+G | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 21 | 10 | 0 | 21 | 10 | 0 | 323 | [14 empty] | 0
P1 |  | T6b | Sanity Test Execution | 3 | 21 | 0 | 0 | 63 | 0 | 0 |  | 2013-04-01: 5 |  | 0
P1 |  | T6c | Monkey Test Execution (Automation) | 2 | 13 | 0 | 0 | 26 | 0 | 0 |  | 2013-04-01: 3 |  | 0
P1 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 21 | 0 | 0 | 21 | 0 | 0 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P1 |  | T6e | Bug Fix | 2.5 | 54 | 13 | 6 | 135 | 32 | 15 | [15 empty] | 0
P2 | 8x30 Tablet with IDH | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0
P2 |  | T6b | Sanity Test Execution | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P2 |  | T6c | Monkey Test Execution (Automation) | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P2 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P2 |  | T6e | Bug Fix | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0
P3 | 8130 TD-SCDMA with IDH | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0
P3 |  | T6b | Sanity Test Execution | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P3 |  | T6c | Monkey Test Execution (Automation) | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P3 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P3 |  | T6e | Bug Fix | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0
P4 | 8230 W+G with IDH | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0
P4 |  | T6b | Sanity Test Execution | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P4 |  | T6c | Monkey Test Execution (Automation) | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P4 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P4 |  | T6e | Bug Fix | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0
P5 | 8x26 SKU1/2 w/C+G DSDA | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 0 | 0 | 10 | 0 | 0 | 10 | 442 | [14 empty] | 0
P5 |  | T6b | Sanity Test Execution | 3 | 0 | 21 | 21 | 0 | 63 | 63 |  | 2013-04-01: 4 |  | 0
P5 |  | T6c | Monkey Test Execution (Automation) | 2 | 0 | 13 | 13 | 0 | 26 | 26 |  | 2013-04-01: 4 |  | 0
P5 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 0 | 21 | 21 | 0 | 21 | 21 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P5 |  | T6e | Bug Fix | 2.5 | 0 | 40 | 45 | 0 | 100 | 112 | [15 empty] | 0
P6 | 8930 TDD LTE w/IDH | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 0 | 10 | 12 | 0 | 10 | 12 | 474 | [14 empty] | 0
P6 |  | T6b | Sanity Test Execution | 3 | 0 | 21 | 21 | 0 | 63 | 63 |  | 2013-04-01: 0 |  | 0
P6 |  | T6c | Monkey Test Execution (Automation) | 2 | 0 | 13 | 13 | 0 | 26 | 26 |  | 2013-04-01: 0 |  | 0
P6 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 0 | 21 | 21 | 0 | 21 | 21 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P6 |  | T6e | Bug Fix | 2.5 | 0 | 41 | 52 | 0 | 102 | 130 | [15 empty] | 0
P7 | 8x10 SKU1/2 w/C+G DSDA | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | [14 empty] | 0
P7 |  | T6b | Sanity Test Execution | 3 | 0 | 0 | 21 | 0 | 0 | 63 |  | 2013-04-01: 0 |  | 0
P7 |  | T6c | Monkey Test Execution (Automation) | 2 | 0 | 0 | 13 | 0 | 0 | 26 |  | 2013-04-01: 0 |  | 0
P7 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 0 | 0 | 21 | 0 | 0 | 21 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P7 |  | T6e | Bug Fix | 2.5 | 0 | 0 | 20 | 0 | 0 | 50 | [15 empty] | 0
P8 | 8926 TDD LTE CMCC | T6a | Modem Auto Test Execution and/or Test Report Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0
P8 |  | T6b | Sanity Test Execution | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P8 |  | T6c | Monkey Test Execution (Automation) | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013-04-01: 0 |  | 0
P8 |  | T6d | Power Test Case Development and Power Sanity Test Execution (Automation) | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
P8 |  | T6e | Bug Fix | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0
Milestone Deliverable Points (MDPs) | [7 empty] | 266 | 474 | 659 | 1399 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0